## tbl_commish_version
tbl_commish_version_id | tbl_commish_version_Number | tbl_commish_version_Summary | tbl_commish_version_Desc | tbl_commish_version_requestedby | tbl_commish_version_requestedDate | tbl_commish_version_Developer | tbl_commish_version_DateComplete | tbl_commish_version_Testedby | tbl_commish_version_TestedDate | tbl_commish_version_TestComments | tbl_commish_version_ReleaseDate | tbl_commish_version_Comments01 | tbl_commish_version_Comments02 | tbl_commish_version_recordDate
1 | 1.96 | Version prior to changes in 2018 | Baseline Version | [10 empty] | 19/02/2018
2 | 1.97 | Prioritised requests detailed in Trello | 1. Updated all blank ABP records to FM Direct (tested and closed by Todd). Note this was a data only change 2. Correct Error on selecting option 3 on main form - had error 94 Null error 3. Created Version History table and form - double click in that area to activate 4. 'Product error when entering Lender - fixed - removed check subroutine until Product is entered and put Lender field after Product field. 5. Fixed default printer error by changing Letter to A4 - on 3 reports 6. Commission updates - Have form loaded with highest status date (ie latest date) - NOT RELEASED - STIL WIP 7. Created Commission Referrer Upfront Ranking report and added to report menu un FM Direct 8. Sorted out day count on both Pipeline and deals settled report to calculate from enquiry date. 9. updated Commission Referrer Upfront Report Summary to sort by upfront consultant commission in descending order | Todd Noble | 2018-02-05 | Nigel Stedman | 2018-02-19 | Todd Noble |  |  | 2018-02-28 |  |  | 19/02/2018
3 | 1.98 | Improved reports | 1. PIPELINE REPORT For this report, can we rename "date" to "status date" and move to after the status column. Also the day count should be from enquiry (like all other reports) Seems to be from submitted date 2. DEALS SETTLED For this report, can we remove the Proposed column. We also need to make sure the date is from enquiry date 3. UPFRONT OUTSTANDING There are a few changes to this report and extra columns to be added. I have included a snapshot of the Commission Input screen and labelled where each column should be pulling the data from. We also want the columns to be moved around with an additional column. I have drawn a diagram of the flow. Any questions, let me know. 4. REFERROR COMMISSION REPORT For the column Nett FMD Upfront, can we change this to be “Gross Upfront”. We would like a new column to be input after Gross Upfront called FMD Upfront. The data for will be generated from Gross Upfront minus Referrer Upfront. Then can we move % paid to Ref to after this new column. 5. LATEST STATUS DATE The problem: The database table has separate fields for different status'. And when you select a different status from the drop down, some code makes visible the corresponding date field…ie all 10 date fields are all on top of each other!. Whilst it all works the table design in this regard is not the best…normally the date and status would be in a separate table linked by say deal id and we could then sort that accordingly. The reason it has been done horizontally (ie all dates in the same table) is to make reports and tabulation easier. So to display the latest date with its corresponding status (which is how it would need to be done) will require some extra code…which I will need to think about a bit more, so as not to make things too complicated. In total I estimate up to 8 hours (incl 2 spent already unravelling the current approach - code, forms. Tables, outputs. | Todd Noble | 2018-03-05 | Nigel Stedman | 2018-03-05 | [6 empty] | 5/03/2018
4 | 2.01 | Improvements and Enhancements | v2.01 Release 1. Searched for spare fields in t_Deal, but only StatusDate_07 (increase) was possible and this had 4 records so added new fields to table including StatusDateLEAD and some spare for future neads. Also added 'LE Lead' to category options and checked that it appeared in the drop down. Changed Code to ensure that is status is LE Lead that the corresponding date field becomes visible on form (after adding this field to form). 2. Added Show Leads Only Checkbox and when clicked on either filters on leads (where no other status except Leads has a date) or removes filters. 3. Added fields on Commission Browse Form to show current status and the date of that status, separate from drop down, which is used to enter dates… 4. Developed Algorithm to calculate the correct status based upon the status date and used that to calculate and display in form 5. Created Leads report based upon Date range, added it to report list and developed query 6. Updated Pipeline reports to show calculated status and highlight when anomalous to latest status and to include selection of Leads as well as to select on calculated status not latest status. 7. Developed Macros to auto fill the corresponding status date field (and make it visible) with todays date in Commission Browse Form 8. Developed Macros for status calcs each way-date to status and status to date. 9. Called up Macro in code for when form opens to display status date corresponding with status field. 10. Updated Deals Settled query and Report in line with the Pipeline reports. 11. Added ‘Deals to track’ Report in Commish to replicate Todd's spreadsheet. Worked on Query to calculated the days between each status change and created report, so it shows up in reports page and has correct group by. Further modified to not select on date range but from 1/11/2017 (Enquiry Date) 12. Functionality for loan amount and actual loan a) update existing data to make actual loan=loan amt. B) change functionality so that went loan amount is entered (or changed) that actual loan is updated to be the same c) Allowed Actual Loan to be updateable without updating loan amount. 13. Changed logic so that for brokerage,difference to estimate is only calculated when the actual is > 0 | Todd | 2018-04-04 | Nigel Stedman | 2018-04-04 | Todd | 2018-04-20 |  | 2018-05-03 |  |  | 4/04/2018
5 | v2.02 | Bug fixes and enhancements | 1. Deal Search-Loan Features - fixed 'repaid exclude' option does not appear to filter records correctly. Also Parameter error message comes up. Changed code from looking for Null in Date Expired to filtering out '06 Re-Financed' and '08 Discharged'. Looked at improving date handling 2. Modified Pipeline report to exclude status of DNP. Looked into status highlighted errors with status and latest status date. Developed algorithm to identify the status date field with the latest date to enable comparison with latest status. Also did same with pipeline summary. 3. Added 10% to actual brokerage for difference calc as they are entered net of GST so that difference would be zero with gst added to actual field. Removed cent fields to ensure a rounding where Calc GST is not precise 4. Added new field DateStatusAIP as part of implementing a new status. Also created a new tick box to allow exclusion from tracking, and macro to enable functionality. Added AIP to Category table, to input form and macro to autofill 5. Modified Deals to track report as per request from Todd, including Averages for each status change, removing Status Calc 4. Investigated dea_con_id where 8 and 722 are used to filter records in most report. Sent a list to Todd for clarification and direction. 5. Investigated Todd's response to the release of v2.01 6. Checked on lead only data and found the latest status was not lead only… so awaiting clarification on the rule. Removed previously requested Lead Only Checkbox and Filter 7. Changed commission form so that when status date is autofilled that only the date is used….currently date and time is used.Additionally searched for and changed any date/time fields to just date. 8. Investigated load error msoutl.olb. Found cause to be new Outlook Library referenced in code (v15 -Outlook 2013) and removed reference. Testing recommenced 9. Reworked algoritm for dates using a simpler approach for pipeline report and input screen…enabling latest status date to be found to derive status for latest date to be compared with currenr status on screen and in reports. Fixed up deal 7611 which had incorrect dates. Changed macros further for autofill for status. | Todd | 2018-05-03 | Nigel Stedman | 2018-05-03 | Todd | 2018-05-14 | Feedback provided | 2018-05-19 |  |  | 3/05/2018
6 | v2.03 Test-b | tidying up from release of 2.02 + additional changes | Refine changes made in 2.02 including 1. Deals to track - fixes and ammendments to days calculations 2. Upfront Outstanding - refinements to calculations and selection criteria and fix of date search which allowed Null for date selection 3. Deals Search - investigated code for selection of loan amount and made made loan amouint fields equal for 4 records 4. Updated Lead report to Active Leads and created a further report for Leads to DNP, put these in the table so that they show up in the reports page 5. Corrected a programming errors in the Pipeline where it was incorrectly showing AIP status as an error |  | 2018-05-19 | Nigel Stedman | 2018-06-19 | Todd |  |  | 2018-06-22 |  |  | 19/05/2018
7 | v2.04 | Minor updates to fix anomalies in reports | 1. Trello Card - Commission Input - Actual Loan - correct formatting issue and position of columns (Commission Outstanding Report 2. Trello Card - Deal Source Report - This report is incorrect. For some reason it is not picking up the chattel finance loans that have settled - Investigate problem - check relevant existing code, check report queries - review selection criteria , check sort keys in report. Make changes, trial, arrange test by Todd: Changed conditions and Gross Upfront Calc to include dea_BrokerageEst_ABP dea_UpfrontEst_ABP 3. Trello Card - Pipeline Report - to investigate further- Removed anomalous field as it is not something FMA require. 4. Trello Card - AIP date is not appearing on the FM Direct Pipeline Report - Time required to investigate : 1hour., fix time 30 mins - Updated query criteria on Status date | Todd | 2019-04-16 | Nigel Stedman | 2019-04-16 | Todd | [5 empty] | 16/04/2019
8 | v2.05 | Minor report enhancements to Reports | 1. Find query and relevant calculations 2. Investigate calculations and logic 3. correct/update conditions and calculations 4. Update report including remove column F and make changes to calcs as per spreadsheet provided 27th August 2019 via Trello 5. Create test version for Todd - update version history and version 5b March2020 Created newer version to meet spreadsheet, then hid last 2 coumns as requested. 6. Create release version for production 7. Release to production. | Todd Noble/Jason | 2019-08-29 | Nigel Stedman | 2019-08-29 | Jason | 2020-03-13 |  | 2020-03-16 |  |  | 29/08/2019
9 | 2.06 | Report Enhancements | Changes to Trail Missing and Referror Rating Summary Reports 1. Find query and relevant calculations 2. Investigate calculations and logic 3. correct/update conditions and calculations 4. Update report including remove column F and make changes to calcs as per spreadsheet provided 27th August 2019 via Trello 5a. Cerated pdfs and provided to Todd on trello for review Sunday 18:50 13/9/2020 5b. Create test version for Todd - update version history and version 5c Created September 2.06 version 6. Create release version for production | Todd/Jason | 2020-09-13 | Nigel | 2020-09-13 | [6 empty] | 13/09/2020